## Ark1
Task/month
February | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Investigate data and features
Information search: Concept of bias in data/algorithms
Report: Description of data
March | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Investigate bias in our data using statistical tools
Report: Description of data
Report: Introduction
Report: Method
Information search: Concept of bias in data/algorithms
Implement and train the algorithm
April | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Investigate bias in our data using statistical tools
Implement adjustments in algorithm *
Find reading material on how to adjust bias in algorithms
Report writing
May | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Report writing
EXAMS
June | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Report writing
Investigate bias in our data using statistical tools
Implement adjustments in algorithm
Prepare presentation
*Article name*
Milestones
6th of march: Found and read a deceant amount of articles ets.
11th of march: Understand the features quete well.
18th march: Hand-in method, introduction, data description
29th of march: Desciption of data done
13th of april: Well on our way implementing adjustments in model, to remove bias
6th of april: Well on our way to finding possible bias in own data using statistics
18th of june: Discussion, method and analysis done